## ProjectManagement
Examining the Association Between Laboratory Biomarkers and Bipolar Disorder Diagnosis: A Data-Driven Analysis
CHL 8010HF2 - Data Wrangling: Group Project |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Group 1 (Selenge Bat-Erdene, Uththami Kukathasan, Victoria Truong, Erwen Wu)
Project start date: | 2025-06-01 |  |  |  |  | June | [34 empty] | July
Scrolling increment: | 0 | time axis 2025-06-01 to 2025-07-26
Milestone description | Category | Assigned to | Progress | Start | Days | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Project Planning & Development | Milestone
Onboarding (TCPS2 Core Ethics Training and PREVENT Study Form) | On Track | Everyone | 100% | 2025-06-02 | 1
Project Kickoff Meeting | On Track | Everyone | 100% | 2025-06-08 | 1
Dataset Exploration & Research Question Identification | On Track | Everyone | 100% | 2025-06-08 | 2
Meeting with Professor Zakaria | On Track | Everyone | 100% | 2025-06-09 | 1
Team Proposal Check-in Meeting | On Track | Everyone | 100% | 2025-06-12 | 1
Project Proposal | Milestone
Literature Review (Lab markers) | On Track | Victoria | 100% | 2025-06-09 | 3
Literature Review (Bipolar disorder) | On Track | Selenge | 100% | 2025-06-09 | 3
Research Question | On Track | Everyone | 100% | 2025-06-08 | 7
Data Sources and Variable Selection | On Track | Uththami | 100% | 2025-06-08 | 8
Initial Data Wrangling & Analysis Plan | On Track | Erwen | 100% | 2025-06-11 | 2
Abstract | On Track | Victoria | 100% | 2025-06-08 | 8
CCS Concepts | On Track | Victoria | 100% | 2025-06-08 | 8
Title | On Track | Everyone | 100% | 2025-06-08 | 8
Keywords | On Track | Everyone | 100% | 2025-06-08 | 8
References & Acknowledgement | On Track | Victoria | 100% | 2025-06-08 | 8
Pre-submission Meeting | On Track | Everyone | 100% | 2025-06-15 | 1
Project Implementation | Milestone | Everyone | 100% | 2025-06-15 | 1
Feasibility study | On Track | Victoria | 100% | 2025-06-25 | 5
Data wrangling | On Track | Victoria | 100% | 2026-06-26 | 5
Missing data | On Track | Uththami | 100% | 2025-06-29 | 2
Exploratory Data Analysis | On Track | Selenge | 100% | 2025-07-01 | 2
Modeling + Exploratory Data Analysis | On Track | Erwen | 100% | 2025-07-01 | 2
Visualizations | On Track | Uththami | 100% | 2025-07-01 | 2
Functions | On Track | Everyone | 100% | 2025-07-07 | 6
Modular coding | On Track | Everyone | 100% | 2025-07-07 | 1
README.md | On Track | Everyone | 100% | 2025-07-13 | 1
main.ipynb | On Track | Everyone | 100% | 2025-07-07 | 6
Supplementary scripts | On Track | Everyone | 100% | 2025-07-07 | 6
Project diagram | On Track | Victoria | 100% | 2025-07-08 | 2
Presentation | Milestone
Slides | Milestone | Everyone | 100% | 2025-07-08 | 5 | bar: S
Script | Milestone | Everyone | 100% | 2025-07-08 | 5
Rehearsal | Milestone | Everyone | 100% | 2025-07-13 | 1
Final Report | Med Risk